## Main
| SDO7 | PROPERTY MANAGEMENT SYSTEM
Tasks |  |  | Chulanga Averil |  |  | Kasundi Maneesha |  |  | Poornami Wijekoon |  |  | Baratha Aberathna
Number |  | Description | Estimate | Actual |  | Estimate | Actual |  | Estimate | Actual |  | Estimate | Actual
Task 1 |  | Requirements Gathering & Documentation
| 1.1 | Preparing Resume & Cover letter | 6 | 5 |  | 5 | 4 |  | 6 | 4 |  | 5 | 3
| 1.2 | Collect information about the project | 6 | 5 |  | 6 | 4 |  | 5 | 4 |  | 4 | 3
| 1.3 | Research project related topics | 7 | 6 |  | 6 | 4 |  | 4 | 4 |  | 5 | 4
| 1.4 | Prepare draft SRS | 9 | 7 |  | 8 | 6 |  | 7 | 6 |  | 8 | 2
| 1.5 | Prepare draft TA | 9 | 8 |  | 8 | 7 |  | 3 | 4 |  | 8 | 2
| 1.6 | Prepare final SRS | 10 | 9 |  | 7 | 5 |  | 6 | 5 |  | 8 | 2
| 1.7 | Prepare final TA | 12 | 10 |  | 10 | 11 |  | 9 | 9 |  | 8 | 2
Task 2 |  | Designing diagrams
| 2.1 | Design usecase diagram for system | 7 |  |  | 6 |  |  | 6 |  |  | 5
| 2.2 | Design class diagram for system | 8 |  |  | 5 |  |  | 6 |  |  | 5
| 2.3 | Design High Level diagram for system | 8 |  |  | 6 |  |  | 5 |  |  | 5
Task 3 |  | Learn tools and concepts
| 3.1 | Learn agile-scrum methodologies | 8 | 7 |  | 4 | 3 |  | 3 | 4 |  | 2 | 2
| 3.2 | Learn about Github functionalities | 9 | 9 |  | 5 | 4 |  | 3 | 5 |  | 4 | 4
| 3.3 | Learn about trello functionalities | 7 | 6 |  | 4 | 3 |  | 4 | 3 |  | 2 | 1
| 3.4 | Learn development technologies (mobile+web) | 9 |  |  | 7 |  |  | 7 |  |  | 8
| 3.5 | Learn language development technologies | 10 |  |  | 3 |  |  | 4 |  |  | 5
Task 4 |  | Design main GUI's of property mangement system
| 4.1 | Study design techniques and design requirements of system | 8 | [5 empty] | 6
| 4.2 | Design main theme of system |  |  |  | 6
| 4.3 | Design home GUI
| 4.4 | Integrate GUI's into one system and connect each of them | [9 empty] | 10
| 4.5 | Finalize and test all the functions of system | 9 |  |  | 8 |  |  | 9 |  |  | 8
Task 5 |  | Backend design and implement database
| 5.1 | Create ER digarm | 6 |  |  | 6 |  |  | 6 |  |  | 6
| 5.2 | Learn about mySQL functionalities | 4 |  |  | 4 |  |  | 4 |  |  | 4
| 5.3 | Create scripts in mySQL | 3 |  |  | 3 |  |  | 3 |  |  | 3
| 5.4 | Execute scripts and implement database | 2 |  |  | 2 |  |  | 2 |  |  | 2
Task 6 |  | Property Management of Property Management System
| 6.1 | Conducting a research and gather information about the property management system | 14 | 12
| 6.2 | Clarifying the functional and non functional requirements by meeting the client. | 6 | 3
| 6.3 | Drawing the necessary UML diagrams according to the function | 12
| 6.4 | Designing GUI according to the specified requirements | 13
| 6.5 | Selecting color code and icons for GUI | 6
| 6.6 | Implementing CRUD functions | 13
| 6.7 | Coding other necessary functions | 10
| 6.8 | Create and execute scripts in mySQL database | 9
| 6.9 | Testing and finalizing the function | 8
Task 7 |  | Booking Management of Property Management System
| 7.1 | Studying required coding technologies and gather tenant requirements | [6 empty] | 8 | 7
| 7.2 | Designing wireframes for booking management GUIs | [6 empty] | 6 | 5
| 7.3 | Designing GUIs for selected requirements and specifications | [6 empty] | 13
| 7.4 | Selecting appropriate color codes and icons for GUIs | [6 empty] | 6
| 7.5 | Creating functions to add and view bookings | [6 empty] | 6
| 7.6 | Creating functions to delete and update bookings | [6 empty] | 12
| 7.7 | Creating function to calculate payments,monthly rentals of the tenants | [6 empty] | 10
| 7.8 | Generating an invoice including payment details | [6 empty] | 8
| 7.9 | Creating and executing scripts in mySQL database | [6 empty] | 9
| 7.1 | Testing and finalizing the function | [6 empty] | 7
Task 8 |  | User Management of Property Management System
| 8.1 | Create function break down list | [9 empty] | 10 | 9
| 8.2 | Draw use case diagram | [9 empty] | 5 | 6
| 8.3 | Create table design scheme | [9 empty] | 5 | 6
| 8.4 | Research about User types of the system | [9 empty] | 5 | 5
| 8.5 | Design wireframe user profile | [9 empty] | 6 | 8
| 8.6 | Design wireframe login | [9 empty] | 6 | 4
| 8.7 | Design GUI's | [9 empty] | 13
Task 9 |  | Bookmark and Save in Property Management System
| 9.1 | Create function break down list | [9 empty] | 10 | 9
| 9.2 | Draw use case diagram | [9 empty] | 5 | 6
| 9.3 | Create table design scheme | [9 empty] | 5 | 6
| 9.4 | Research about UX in bookmarking,Save property | [9 empty] | 6 | 5
| 9.5 | Design wireframe my bookmarks | [9 empty] | 8 | 8
| 9.6 | Design GUI's | [9 empty] | 13
| 9.7 | Ajax review for bookmark function | [9 empty] | 6
Task 10 |  | Review and Commenting in Property Management System
| 10.1 | Study about review and commenting function details and functional requirements |  |  |  | 10 | 8
| 10.2 | Design wireframe for Review and commenting GUI |  |  |  | 5 | 4
| 10.3 | Select appropriate colors and icons for Review and commenting GUI |  |  |  | 6
| 10.4 | Design GUI of Review and commenting |  |  |  | 14
| 10.5 | Create functions to add and view reviews and comments |  |  |  | 9
| 10.6 | Create functions to delete and update reviews and comments |  |  |  | 8
| 10.7 | Create functions to rate the system |  |  |  | 7
| 10.8 | Create other necessary functions |  |  |  | 9
| 10.9 | Create and execute scripts in mySQL database |  |  |  | 8
| 10.1 | Test and finalize function |  |  |  | 6
Task 11 |  | Search in Property Management System
| 11.1 | Gathering search management function details and requirements | [6 empty] | 9 | 6
| 11.2 | Designing wireframes for search management | [6 empty] | 6 | 4
| 11.3 | Designing GUIs for Search management function | [6 empty] | 6
| 11.4 | Implementing the function to search properties | [6 empty] | 9
| 11.5 | Implementing CRUD functions | [6 empty] | 10
| 11.6 | Creating other required codes for the function | [6 empty] | 9
| 11.7 | Creating and executing scripts in mySQL database | [6 empty] | 8
| 11.8 | Testing and finalizing function | [6 empty] | 6
Task 12 |  | Preferences Management in Property Management System
| 12.1 | Search for preference management function details and requirements |  |  |  | 9 | 6
| 12.2 | Study required GUI design tehnologies for function and design wireframe |  |  |  | 7 | 5
| 12.3 | Select appropriate icons and colors for GUI |  |  |  | 4
| 12.4 | Design GUI of preferences management for selected guidelines |  |  |  | 14
| 12.5 | Create functions to get user preferences and sort it in results |  |  |  | 10
| 12.6 | Create other required functions |  |  |  | 9
| 12.7 | Create and execute scripts in mySQL database |  |  |  | 8
| 12.8 | Test and finalize function |  |  |  | 5
|  |  | 248 | 87 | 0 | 235 | 74 | 0 | 256 | 70 | 0 | 218 | 97 | 0
Approval of the supervisor: